## Project Schedule
Project Grocery Store
[Company Name]: -
| Project Start Date | 2023-06-05
| Project Lead | Pornmook Wasthong
| Task Name | Plan Start | Duration | Staff Name | Actual % of Work | Actual Start | End | % Done
1 | Project Planning Activities |  | (day)
1.1 | Define the Problem
1.1.1 | Meet with stakeholder | 2023-08-02 | 1 | Pornmook Wasthong | 100% | 2023-08-02 | 2023-08-02 | 100%
1.1.2 | Definie scope | 2023-08-03 | 1 | Pornmook Wasthong | 20% | 2023-08-03 | 2023-08-03 | 100%
1.1.3 | Analyze problem | 2023-08-04 | 2 | Pornmook Wasthong | 100% | 2023-08-05 | 2023-08-05 | 100%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%
|  |  |  | Pannawat khookaew | 20%
1.1.4 | Identify business benefits | 2023-08-04 | 2 | Pornmook Wasthong | 50% | 2023-08-05 | 2023-10-05 | 100%
|  |  |  | Napatsorn Chimwiset | 50%
1.1.5 | Identify system capabilities | 2023-08-05 | 2 | Pornmook Wasthong | 50% | 2023-08-05 | 2023-10-05 | 100%
|  |  |  | Pannawat khookaew | 50%
1.1.6 | Develop context diagram | 2023-08-06 | 4 | Pornmook Wasthong | 100% | 2023-08-07 | 2023-11-07 | 100%
1.2 | Produce the project schedule
1.2.1 | Develop WBS | 2023-08-09 | 1 | Pavida Jainol | 100% | 2023-08-09 | 2023-08-09 | 100%
1.2.2 | Estimate task durations | 2023-08-11 | 1 | Pannawat khookaew | 20% | 2023-08-12 | 2023-08-11 | 100%
|  |  |  | Pornmook Wasthong | 20%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%
1.2.3 | Determine sequences | 2023-08-11 | 1 | Pornmook Wasthong | 100% | 2023-08-12 | 2023-08-12 | 100%
1.2.4 | Assign Resource | 2023-08-12 | 1 | Pannawat khookaew | 20% | 2023-08-13 | 2023-08-13 | 100%
|  |  |  | Pornmook Wasthong | 20%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%
1.3 | Confirm project feasibility
1.3.1 | Identify intangible cost/benefit | 2023-08-15 | 1 | Pannawat khookaew | 20% | 2023-08-15 | 2023-08-15 | 100%
|  |  |  | Pornmook Wasthong | 20%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%
1.3.2 | Estimate tangible benefits | 2023-08-16 | 1 | Pannawat khookaew | 20% | 2023-08-16 | 2023-08-16 | 100%
|  |  |  | Pornmook Wasthong | 20%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%
1.3.3 | Calculate cost/benefits | 2023-08-17 | 1 | Pornmook Wasthong | 100% | 2023-08-17 | 2023-08-17 | 100%
1.3.4 | Organization feasibility | 2023-08-17 | 2 | Pornmook Wasthong | 100% | 2023-08-17 | 2023-08-17 | 100%
1.3.5 | Technical feasibility | 2023-08-18 | 3 | Pannawat khookaew | 20% | 2023-08-18 | 2023-08-18 | 100%
|  |  |  | Pornmook Wasthong | 20%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%
1.3.6 | Evaluate resource availability | 2023-08-19 | 1 | Pornmook Wasthong | 100% | 2023-08-20 | 2023-08-20 | 100%
1.3.7 | Risk analysis | 2023-08-20 | 2 | Pannawat khookaew | 20% | 2023-08-20 | 2023-08-20 | 100%
|  |  |  | Pornmook Wasthong | 20%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%
1.4 | Staff the project
1.4.1 | Develop resource plan | 2023-08-22 | 1 | Pornmook Wasthong | 100% | 2023-08-22 | 2023-08-22 | 100%
1.4.2 | Find project team | 2023-08-23 | 3 | Pornmook Wasthong | 100% | 2023-08-23 | 2023-08-23 | 100%
1.4.3 | Appoint a coordinator with user | 2023-08-24 | 1 | Pornmook Wasthong | 100% |  |  | 100%
1.4.4 | Training the project team | 2023-08-25 | 5 | Pornmook Wasthong | 100% |  |  | 100%
1.5 | Launch the project
1.5.1 | Summary project | 2023-08-29 | 1 | Pannawat khookaew | 20% | 2023-10-18 | 2023-10-10 | 100%
|  |  |  | Pornmook Wasthong | 20%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%
1.5.2 | Prepare project presentation to stakeholder | 2023-08-30 | 3 | Pornmook Wasthong | 100% | 2023-10-18 | 2023-10-20 | 100%
1.5.3 | Testing project | 2023-09-01 | 7 | Pannawat khookaew | 20% | 2023-10-18 | 2023-10-19 | 100%
|  |  |  | Pornmook Wasthong | 20%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%
1.5.4 | Define problem and develop the project | 2023-09-04 | 10 | Pannawat khookaew | 20% | 2023-10-18 | 2023-10-21 | 100%
|  |  |  | Pornmook Wasthong | 20%
|  |  |  | Pavida Jainol | 20%
|  |  |  | Napatsorn Chimwiset | 20%

## Feasibility
Feasibility year 1-8
Year
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Benefits
Increase sales |  | 500000 | 540000 | 580000 | 610000 | 650000 | 690000 | 730000 | 770000 | 5070000
Reduction delivery cost |  | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 144000
Reduction product waste |  | 10000 | 10000 | 12000 | 10000 | 10000 | 12000 | 10000 | 10000 | 84000
Reduction problem report |  | 5000 | 5000 | 7000 | 5000 | 5000 | 7000 | 5000 | 5000 | 44000
Total benefits |  | 533000 | 573000 | 617000 | 643000 | 683000 | 727000 | 763000 | 803000 | 5342000
Delivery costs
Fuel |  | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 144000
Insurance |  | 32789.04 | 32789.04 | 32789.04 | 32789.04 | 32789.04 | 32789.04 | 32789.04 | 32789.04 | 262312.32
Delivery driver |  | 142000 | 142000 | 147000 | 142000 | 142000 | 147000 | 142000 | 142000 | 1146000
Total Delivery costs |  | 192789.04 | 192789.04 | 197789.04 | 192789.04 | 192789.04 | 197789.04 | 192789.04 | 192789.04 | 1552312.32
Store costs
Hardware
- 2 Cash registers @ 8,800 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17600
- Computers | 20790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20790
- Barcode warehouse scanner | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600
Employee |  | 160000 | 160000 | 165000 | 160000 | 160000 | 165000 | 160000 | 160000 | 1290000
Costs of utilities |  | 66972 | 68972 | 70972 | 72972 | 74972 | 76972 | 78972 | 80972 | 591776
Total store costs | 41990 | 226972 | 228972 | 235972 | 232972 | 234972 | 241972 | 238972 | 240972 | 1923766
Website maintenance costs
Hardware
- Computers | 20790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20790
Software |  | 13143 | 13143 | 13143 | 13143 | 13143 | 13143 | 13143 | 13143 | 105144
Server |  | 2990 | 2990 | 2990 | 2990 | 2990 | 2990 | 2990 | 2990 | 23920
Developers |  | 180000 | 180000 | 185000 | 180000 | 180000 | 185000 | 180000 | 180000 | 1450000
Total development costs | 20790 | 196133 | 196133 | 201133 | 196133 | 196133 | 201133 | 196133 | 196133 | 1599854
Total costs | 62780 | 615894.04 | 617894.04 | 634894.04 | 621894.04 | 623894.04 | 640894.04 | 627894.04 | 629894.04 | 5075932.32
Total benefits – Total costs | -62780 | -82894.04 | -44894.04 | -17894.04 | 21105.96 | 59105.96 | 86105.96 | 135105.96 | 173105.96 | 92961.72
Cumulative Net Cash Flow | -62780 | -145674.04 | -190568.08 | -208462.12 | -187356.16 | -128250.2 | -42144.24 | 92961.72 | 266067.68
Return on Investment (ROI) | 0.18% (92,961.72/5,075,932.32)
Break – Event Point | 6.31 year (costs are fully recovered in year 7; [135,105.96 – 92,961.72]/135,105.96 = .31)
| 0.018314 | Year 2: 0.31193